## Terminal_Application
Task ID | Created At | Completed At | Last Modified | Name | Section/Column | Assignee | Assignee Email | Start Date | Due Date | Tags | Notes | Projects | Parent Task | Priority
1200613078247360 | 2021-07-16 |  | 2021-07-16 | Nice-to-haves | To do |  |  |  |  | code |  | Terminal Application |  | Low
1200613078247360 | 2021-07-16 |  | 2021-07-16 | Better selection of words for 1 player mode | [5 empty] | code |  |  | Nice-to-haves
1200613078247360 | 2021-07-16 |  | 2021-07-16 | Ability to have spaces and hyphens in 2 player mode | [5 empty] | code |  |  | Nice-to-haves
1200613078247360 | 2021-07-16 |  | 2021-07-16 | Keep list of words guessed | [5 empty] | code |  |  | Nice-to-haves
1200575748956880 | 2021-07-10 |  | 2021-07-10 | Submit ZIP file | To do |  |  |  | 2021-07-17 | project management | Your source control repository should be zipped and submitted via the Canvas LMS platform. The Software Development Plan must be submitted as a plain-text file using markdown Your application, exports from project management software, screenshots, and any other part of your submission should be in your source control repository. Any file you submit should have a filename which reflects what the file is, contain your name, and the requirements code it relates to. For example: bill-lastname-T1A2-13-project-mgt-checklist1.jpg | Terminal Application |  | High
1200575748956870 | 2021-07-10 | 2021-07-16 | 2021-07-16 | Implement Application | Complete |  |  |  | 2021-07-16 | project management | Implement all features in the software development plan you have designed. You must utilise a range of programming concepts and structures using Python 3 such as: - variables and variable scope - loops and conditional control structures - error handling Apply all style and conventions for the programming language consistently to all code produced. Creates an application which runs without error and has features that are consistent with the development plan. | Terminal Application |  | High
1200575748956870 | 2021-07-10 | 2021-07-16 | 2021-07-16 | Help File |  |  |  |  | 2021-07-16 | project management | Design a help file which includes a set of instructions which accurately describe how to use and install the application. You must include: - steps to install the application - any dependencies required by the application to operate - any system/hardware requirements - a written explanation of the different features of the application The help file should be 100 - 200 words. |  | Implement Application | High
1200575748956870 | 2021-07-10 | 2021-07-16 | 2021-07-16 | Developer Operations | Complete |  |  |  | 2021-07-16 | project management |  | Terminal Application |  | High
1200575748956880 | 2021-07-10 | 2021-07-15 | 2021-07-15 | Source Control |  |  |  |  | 2021-07-16 | project management | Utilise source control throughout the development of the application by: - making regular commits (at least 20 commits) with a commit message that summarises the changes |  | Developer Operations | High
1200575748956880 | 2021-07-10 | 2021-07-15 | 2021-07-15 | Project Management |  |  |  |  | 2021-07-16 | project management | Utilise a project management platform to track the development of the application by: - having features itemised and broken down into checklists - setting deadlines, duration or a time-frame for each feature or task - prioritising tasks You must submit screenshots, or a valid export from a project management application to satisfy this requirement. If you are using a non-standard project management application, please discuss with your trainer whether they can access the file. If in doubt, screen capture your project management application and submit screen captures. |  | Developer Operations | High
1200575748956880 | 2021-07-10 | 2021-07-16 | 2021-07-16 | Operating System features |  |  |  |  | 2021-07-15 | project management | Utilise operating system features to facilitate the building and testing of the application by: - creating a wrapper script which turns the application into an executable - and/or creating a script which performs the tests you have specified in your design document A good mark can be achieved by executing either of these two options in a sophisticated fashion. For maximum marks, attempt both. You must submit a script file in with your source control repository to satisfy this requirement. |  | Developer Operations | High
1200575748956870 | 2021-07-10 | 2021-07-16 | 2021-07-16 | Test Application | Complete |  |  |  | 2021-07-16 | project management | Design TWO tests which check that the application is running as expected. Each test should: - cover a different feature of the application - state what is being tested - provide at least TWO test cases and the expected results for each test case An outline of the testing procedure and cases should be included with the source code of the application and written in markdown. | Terminal Application |  | High
1200575748956870 | 2021-07-10 | 2021-07-15 | 2021-07-15 | Test 1 - reveal word as guessed |  |  |  |  | 2021-07-13 | project management | 2 player mode: Test that a long word with repeated letters displays properly as those letters are guessed. |  | Test Application | High
1200575748956870 | 2021-07-10 | 2021-07-16 | 2021-07-16 | Test 2 - play again |  |  |  |  | 2021-07-16 | project management |  |  | Test Application | High
1200587327000500 | 2021-07-12 | 2021-07-16 | 2021-07-16 | Ask player if they want to play again (Y/N) | Complete |  |  |  | 2021-07-14 | code |  | Terminal Application |  | Low
1200587327000470 | 2021-07-12 | 2021-07-16 | 2021-07-16 | Print snowman status & word status | Complete |  |  |  | 2021-07-14 | code |  | Terminal Application |  | High
1200587327000490 | 2021-07-12 | 2021-07-15 | 2021-07-16 | After every guess, clear the screen and show an updated screen | Complete |  |  |  | 2021-07-14 | code |  | Terminal Application | Print snowman status & word status | High
1200587327000490 | 2021-07-12 | 2021-07-15 | 2021-07-16 | After every correct guess, print the snowman's status and the word with the correct letters filled in | Complete |  |  |  | 2021-07-14 | code |  | Terminal Application | Print snowman status & word status | High
1200587327000490 | 2021-07-12 | 2021-07-16 | 2021-07-16 | If all letters are guessed correctly, print a "you won" screen | Complete |  |  |  | 2021-07-14 | code |  | Terminal Application | Print snowman status & word status | High
1200587327000500 | 2021-07-12 | 2021-07-15 | 2021-07-16 | After every incorrect guess, print the snowman with one more body part missing and the word with the correct guesses filled in | Complete |  |  |  | 2021-07-14 | code |  | Terminal Application | Print snowman status & word status | High
1200587327000500 | 2021-07-12 | 2021-07-16 | 2021-07-16 | After seven incorrect guesses, print a puddle and the completed word | Complete |  |  |  | 2021-07-14 | code |  | Terminal Application | Print snowman status & word status | High
1200587327000470 | 2021-07-12 | 2021-07-15 | 2021-07-15 | Get letter guesses from player | Complete |  |  |  | 2021-07-13 | code |  | Terminal Application |  | High
1200587327000490 | 2021-07-12 | 2021-07-15 | 2021-07-15 | Ensure guess is either one letter or equal to the length of the answer | Complete |  |  |  | 2021-07-13 | code |  | Terminal Application | Get letter guesses from player | High
1200587327000490 | 2021-07-12 | 2021-07-15 | 2021-07-15 | Ensure guess is only letters | Complete |  |  |  | 2021-07-13 | code |  | Terminal Application | Get letter guesses from player | High
1200587327000490 | 2021-07-12 | 2021-07-15 | 2021-07-15 | Convert guess to upper case | Complete |  |  |  | 2021-07-13 | code |  | Terminal Application | Get letter guesses from player | High
1200587327000490 | 2021-07-12 | 2021-07-15 | 2021-07-15 | Add guesses to a guessed list | Complete |  |  |  | 2021-07-13 | code |  | Terminal Application | Get letter guesses from player | High
1200587327000490 | 2021-07-12 | 2021-07-15 | 2021-07-15 | Check guesses are not already on the guessed list | Complete |  |  |  | 2021-07-13 | code |  | Terminal Application | Get letter guesses from player | High
1200587327000460 | 2021-07-12 | 2021-07-15 | 2021-07-15 | Get word or words | Complete |  |  |  | 2021-07-13 | code |  | Terminal Application |  | High
1200587327000480 | 2021-07-12 | 2021-07-15 | 2021-07-15 | Check entered words are only letters, spaces or hyphens | Complete |  |  |  | 2021-07-13 | code |  | Terminal Application | Get word or words | High
1200587327000480 | 2021-07-12 | 2021-07-15 | 2021-07-15 | Convert to upper case | Complete |  |  |  | 2021-07-13 | code |  | Terminal Application | Get word or words | High
1200587327000460 | 2021-07-12 | 2021-07-15 | 2021-07-15 | Print ascii art snowman and blank spaces for missing letters | Complete |  |  |  | 2021-07-13 | code |  | Terminal Application |  | High
1200587327000480 | 2021-07-12 | 2021-07-15 | 2021-07-15 | Underscores for missing letters | Complete |  |  |  | 2021-07-13 | code |  | Terminal Application | Print ascii art snowman and blank spaces for missing letters | High
1200587327000480 | 2021-07-12 | 2021-07-15 | 2021-07-15 | Show spaces & hyphens | Complete |  |  |  | 2021-07-13 | code |  | Terminal Application | Print ascii art snowman and blank spaces for missing letters | High
1200575748956860 | 2021-07-10 | 2021-07-15 | 2021-07-15 | Production Log | Complete |  |  |  | 2021-07-15 | project management | Write TWO status updates on your application. You must write a status update when: - you significantly change a feature or your implementation plan at any point - encounter a significant issue, challenge or roadblock - are halfway through implementing the features - prior to / after testing the application You should submit these logs throughout the course of developing your application. Each status report should be between 100 - 200 words. The Development Log should be written in markdown and placed in a file named development-log.md in the root of your source control repository. Ensure you put the date of the log at the top of each log entry. Please send your log to your educator as a markdown file as you complete them. This is so we can provide you with feedback. | Terminal Application |  | High
1200575748956900 | 2021-07-10 | 2021-07-12 | 2021-07-12 | Status update 1 |  |  |  |  | 2021-07-12 | project management |  |  | Production Log | High
1200575748956900 | 2021-07-10 | 2021-07-15 | 2021-07-15 | Status update 2 |  |  |  |  | 2021-07-15 | project management |  |  | Production Log | High
1200587327000460 | 2021-07-12 | 2021-07-13 | 2021-07-13 | 1 player or 2 | Complete |  |  |  | 2021-07-12 | code |  | Terminal Application |  | Medium
1200587327000480 | 2021-07-12 | 2021-07-13 | 2021-07-13 | Create list of possible words to choose from randomly if only 1 player |  |  |  |  | 2021-07-12 | code |  |  | 1 player or 2 | Medium
1200587327000460 | 2021-07-12 | 2021-07-12 | 2021-07-12 | Create ascii art | Complete |  |  |  | 2021-07-12 | code |  | Terminal Application |  | High
1200587327000470 | 2021-07-12 | 2021-07-12 | 2021-07-12 | Completed snowman |  |  |  |  | 2021-07-12 | code |  |  | Create ascii art | High
1200587327000480 | 2021-07-12 | 2021-07-12 | 2021-07-12 | Snowman without hat |  |  |  |  | 2021-07-12 | code |  |  | Create ascii art | High
1200587327000480 | 2021-07-12 | 2021-07-12 | 2021-07-12 | Snowman without scarf |  |  |  |  | 2021-07-12 | code |  |  | Create ascii art | High
1200587327000480 | 2021-07-12 | 2021-07-12 | 2021-07-12 | Snowman without eyes |  |  |  |  | 2021-07-12 | code |  |  | Create ascii art | High
1200587327000480 | 2021-07-12 | 2021-07-12 | 2021-07-12 | Snowman without nose |  |  |  |  | 2021-07-12 | code |  |  | Create ascii art | High
1200587327000470 | 2021-07-12 | 2021-07-12 | 2021-07-12 | Snowman without head |  |  |  |  | 2021-07-12 | code |  |  | Create ascii art | High
1200587327000470 | 2021-07-12 | 2021-07-12 | 2021-07-12 | Snowman without arms |  |  |  |  | 2021-07-12 | code |  |  | Create ascii art | High
1200587327000470 | 2021-07-12 | 2021-07-12 | 2021-07-12 | Snowman without torso |  |  |  |  | 2021-07-12 | code |  |  | Create ascii art | High
1200587327000470 | 2021-07-12 | 2021-07-12 | 2021-07-12 | Puddle |  |  |  |  | 2021-07-12 | code |  |  | Create ascii art | High
1200587327000540 | 2021-07-12 | 2021-07-12 | 2021-07-12 | Welcome screen |  |  |  |  | 2021-07-12 |  |  |  | Create ascii art
1200575748956840 | 2021-07-08 | 2021-07-10 | 2021-07-10 | Write out requirements in Asana | Complete |  |  |  | 2021-07-09 | project management |  | Terminal Application |  | High
1200575748956820 | 2021-07-08 | 2021-07-10 | 2021-07-10 | Get github backups working | Complete |  |  |  | 2021-07-09 | project management |  | Terminal Application |  | High
1200575748956830 | 2021-07-08 | 2021-07-10 | 2021-07-10 | Send idea to Oliver | Complete |  |  |  | 2021-07-08 | project management |  | Terminal Application |  | High
1200575748956820 | 2021-07-08 | 2021-07-08 | 2021-07-10 | Choose application | Complete |  |  |  | 2021-07-08 | project management | Brainstorm ideas What are the minimum viable features? Nice to have? Dream? What sort of errors are you likely to run into? Scaffold a rough idea of what your program flow might look like Get this, do this, output this | Terminal Application |  | High
1200575748956820 | 2021-07-08 | 2021-07-08 | 2021-07-10 | Gymnastics competition roster | [5 empty] | project management |  |  | Choose application
1200575748956820 | 2021-07-08 | 2021-07-08 | 2021-07-10 | Raffle | [5 empty] | project management |  |  | Choose application
1200575748956830 | 2021-07-08 | 2021-07-08 | 2021-07-10 | Random password generator | [5 empty] | project management |  |  | Choose application
1200575748956830 | 2021-07-08 | 2021-07-08 | 2021-07-10 | Hangman | [5 empty] | project management |  |  | Choose application
1200575748956860 | 2021-07-10 | 2021-07-12 | 2021-07-12 | Implementation Plan | Complete |  |  |  | 2021-07-11 | project management | Develop an implementation plan which: - outlines how each feature will be implemented and a checklist of tasks for each feature - prioritise the implementation of different features, or checklist items within a feature - provide a deadline, duration or other time indicator for each feature or checklist/checklist-item You must submit this as a written document, ideally in a tabular format, and it is suggested that you enter your checklists into an appropriate project management application to assist you in completing T1A2-10. Your checklists for each feature should have at least 5 items. | Terminal Application |  | High
1200575748956850 | 2021-07-10 | 2021-07-12 | 2021-07-12 | Software development plan | Complete |  |  |  | 2021-07-11 | project management | Design a software development plan for a terminal application This task should be written in a single document in a report format with headings. It is suggested that this document is placed in the root of your source control repository, and that you write it in markdown. NOTE: we do not accept submission of Word, Pages or Open office documents. We will only accept PDFs, or markdown files for written assessments. | Terminal Application |  | High
1200575748956860 | 2021-07-10 | 2021-07-12 | 2021-07-12 | Statement of Purpose and Scope | Complete |  |  |  | 2021-07-11 | project management | Develop a statement of purpose and scope for your application. It must include: - describe at a high level what the application will do - identify the problem it will solve and explain why you are developing it - identify the target audience - explain how a member of the target audience will use it | Terminal Application | Software development plan | High
1200575748956860 | 2021-07-10 | 2021-07-12 | 2021-07-12 | Features | Complete |  |  |  | 2021-07-11 | project management | Develop a list of features that will be included in the application. It must include: - at least THREE features - describe each feature Ensure that your features include the following language elements and concepts: - use of variables and the concept of variable scope - loops and conditional control structures - error handling Note: If the features you described do not require you to use all of the above it is likely that your application is not sophisticated enough. Consult with your educator to check your features are sufficient to address the assessment criteria. | Terminal Application | Software development plan | High
1200575748956860 | 2021-07-10 | 2021-07-12 | 2021-07-12 | User Interaction and Experience | Complete |  |  |  | 2021-07-11 | project management | Develop an outline of the user interaction and experience for the application. Your outline must include: - how the user will find out how to interact with / use each feature - how the user will interact with / use each feature - how errors will be handled by the application and displayed to the user | Terminal Application | Software development plan | High
1200575748956860 | 2021-07-10 | 2021-07-12 | 2021-07-12 | Control Flow Diagram | Complete |  |  |  | 2021-07-11 | project management | Develop a diagram which describes the control flow of your application. Your diagram must: - show the workflow/logic and/or integration of the features in your application for each feature. - utilise a recognised format or set of conventions for a control flow diagram, such as UML. Please provide an image file or PDF of your diagram. | Terminal Application | Software development plan | High